## BOM
Project ROCKY - Pebble (subscale radial pentapod) - Bill of Materials
Prices are July-2026 US estimates (see Source column). Blue cells = edit me (qty, unit price, status). Line totals & rollups are formulas. Already owned (excluded): printer hot ends/nozzles, PLA + CF-PLA + purple PETG stock, Xbox Elite controller.
Phase / Batch | Category | Item | Spec / Notes | Qty | Unit $ (est) | Line Total $ | Source (Jul 2026) | Status
0-Foundations | Materials | TPU filament 1 kg (95A) | Foot pads, bumpers, gaskets - only filament type not in current stock | 1 | 25 | 25 | Amazon; est | to buy
0-Foundations | Materials | PETG restock 1 kg x2 | OPTIONAL: when the purple runs out; PLA/CF-PLA cover jigs + Phase-1 links meanwhile | 2 | 20 | 40 | Amazon; est; OPTIONAL | to buy
0-Foundations | Tools | Digital calipers 150mm | OPTIONAL: skip if owned - essential for CAD fit checks | 1 | 22 | 22 | Amazon; est; OPTIONAL | to buy
1-One True Leg | Actuators | Feetech/Waveshare ST3215 bus servo, 12V 30kg.cm | MUST be 12V variant; magnetic encoder, 1Mbps TTL bus; $16.99-21.99 depending on vendor | 4 | 19 | 76 | waveshare.com/st3215-servo.htm; Amazon B0CFY52HVV | to buy
1-One True Leg | Actuators | Feetech SCS0009 micro bus servo | Hand/claw drive prototype; same TTL bus, 2.3 kg.cm | 1 | 12 | 12 | Seeed SCS0009 p-6535; Amazon 2-pack; est | to buy
1-One True Leg | Electronics | Waveshare Bus Servo Adapter (A) | UART<->TTL bus + servo power distribution | 1 | 7 | 7 | waveshare.com/bus-servo-adapter-a.htm; est | to buy
1-One True Leg | Electronics | Bench PSU 12V 10A | Powers leg jig before batteries exist; reused as charger supply | 1 | 26 | 26 | Amazon; est | to buy
1-One True Leg | Mechanical | Compression/die spring assortment | SEA shin: ~7mm travel at 8-12N preload | 1 | 10 | 10 | Amazon/AliExpress; est | to buy
1-One True Leg | Mechanical | Carbon fiber tube 8-10mm OD x2 | Tibia shins | 2 | 7 | 14 | Amazon/AliExpress; est | to buy
1-One True Leg | Hardware | M2/M2.5/M3 screw + nut assortment | Mostly M3; includes locknuts | 1 | 25 | 25 | Amazon; est | to buy
1-One True Leg | Hardware | 683ZZ bearings 3x7x3 (10-pack) | Coxa yaw shaft support | 1 | 8 | 8 | Amazon; est | to buy
1-One True Leg | Hardware | M3 heat-set inserts (100) | For parts opened repeatedly | 1 | 12 | 12 | Amazon; est | to buy
1-One True Leg | Hardware | Misc: wire, JST leads, couplers | Phase-1 consumables | 1 | 10 | 10 | est | to buy
1-One True Leg | Electronics | USB-UART dongle (CP2102/CH343) | Drive the servo bus straight from the laptop for bench work, before the Pi exists | 1 | 8 | 8 | Amazon; est | to buy
2-Pebble Walks | Actuators | ST3215 12V 30kg.cm (11 more + 2 spares) | Brings leg-servo total to 15 + 2 spares | 13 | 19 | 247 | waveshare.com/st3215-servo.htm | to buy
2-Pebble Walks | Actuators | SCS0009 micro bus servo (4 more) | Completes 5 hands | 4 | 12 | 48 | Seeed/Amazon; est | to buy
2-Pebble Walks | Compute | Raspberry Pi 5, 8GB | Feb-2026 price after memory-shortage rises (was $80) | 1 | 125 | 125 | Tom's Hardware Feb-2026; raspberrypi.com | to buy
2-Pebble Walks | Compute | microSD 64GB A2 + Pi active cooler | Boot media + thermals | 1 | 18 | 18 | Amazon; est | to buy
2-Pebble Walks | Power | 3S LiPo 5200mAh 30C+ XT60 x2 | ~45 min walking each at 80% DoD | 2 | 37 | 74 | Amazon (Zeee/HRB class); est | to buy
2-Pebble Walks | Power | LiPo balance charger + charge bag | B6AC/ISDT class | 1 | 43 | 43 | Amazon; est | to buy
2-Pebble Walks | Power | 5V/5A buck converter | Pi 5 supply from 3S rail | 1 | 16 | 16 | Amazon; est | to buy
2-Pebble Walks | Power | XT60 pigtails, inline fuse + 15A fuses, power switch | Power tree per plan section 4 | 1 | 26 | 26 | Amazon; est | to buy
2-Pebble Walks | Wiring | Silicone wire kit 16/20/24 AWG + servo extension leads | Harness | 1 | 30 | 30 | Amazon; est | to buy
2-Pebble Walks | Power | Inline XT60 wattmeter/power analyzer | OPTIONAL: live A/W/Wh readout - validates the power budget, catches sick servos early | 1 | 12 | 12 | Amazon; est; OPTIONAL | to buy
3-Pebble Senses | Sensors | Adafruit BNO085 9-DOF IMU | On-chip fusion -> quaternions over I2C | 1 | 24.95 | 24.95 | adafruit.com/product/4754 | to buy
3-Pebble Senses | Sensors | Pi Camera Module 3 Wide + 500mm cable | On mini pan turret (uses 1 SCS0009) | 1 | 41 | 41 | raspberrypi.com; est | to buy
3-Pebble Senses | Sensors | Pan-turret SCS0009 + microswitches (10pk) | Foot contact switches in SEA cartridges | 1 | 20 | 20 | Seeed/Amazon; est | to buy
3-Pebble Senses | Sensors | OAK-D Lite depth camera | OPTIONAL: stereo depth + on-camera NN | 1 | 128 | 128 | shop.luxonis.com; verify current price; OPTIONAL | to buy
3-Pebble Senses | Sensors | 360-deg lidar (LD19/RPLidar-C1 class) | OPTIONAL: SLAM/nav for a robot with no front | 1 | 99 | 99 | RobotShop/Amazon; est; OPTIONAL | to buy
4-Pebble Thinks | Audio | I2S amp (MAX98357A) + 4-ohm speaker | Chord-speak voice | 1 | 14 | 14 | Adafruit/Amazon; est | to buy
4-Pebble Thinks | Audio | USB mini microphone | Voice commands (or use laptop mic) | 1 | 15 | 15 | Amazon; est | to buy
[5 empty] | GRAND TOTAL (all items): | 1275.95

## Summary
Project ROCKY - Budget Summary
Rolls up live from the BOM sheet via SUMIFS - edit quantities/prices there.
Phase / Batch | Gate (what must work before next spend) | Subtotal $ | Cumulative $
0-Foundations | Prusa prints PETG cleanly; pentapod walks in MuJoCo sim | 87 | 87
1-One True Leg | Bench leg tracks ROS 2 trajectories; SEA shin survives impacts; claw prototype works | 208 | 295
2-Pebble Walks | Stands, wave-gait walks omnidirectionally, teleop | 639 | 934
3-Pebble Senses | IMU-stabilized body; terrain adaptation via foot contacts; camera streams | 312.95 | 1246.95
4-Pebble Thinks | Laptop VLM agent drives robot skills by voice/vision; chord-speak | 29 | 1275.95
TOTAL |  | 1275.95
Budget envelope | 1500
Headroom remaining | 224.05
Trim levers if needed:
Buy ST3215 direct from Waveshare (~$17) or AliExpress official FEETECH store (~$14-16): saves $30-80 across 17 units - VERIFY 12V/30kg.cm variant
Skip the 2 spare servos initially: -$38 (riskier)
Defer OAK-D Lite and lidar (yellow OPTIONAL rows): -$227; or eBay a used robot-vacuum lidar (~$15-30) for Phase 3
One LiPo instead of two to start: -$37
Per-leg marginal cost after leg #1: ~ $70-75 (3x ST3215 + 1x SCS0009); everything else in Batch 1 is one-time shared kit
Legend: blue = editable input (qty, unit price, status, envelope); black = formula; yellow rows on BOM = optional items.